## Budget
SEMANTRAL WORK PLAN (60m)
Work package | Pillar / objective | Role | Headcount | Start month | End month | Y1 PM | Y2 PM | Y3 PM | Y4 PM | Y5 PM | Total | PM Workload % | Total cost (€) | Notes
WP0–WP5 | Coordination, P1, P2, P3, P4 | PI | 1 | 1 | 60 | 12 | 12 | 12 | 12 | 12 | 60 | 55% | 179173.0138 | Scientific leadership, supervision and integration across m1–m60.
WP1 | P1 | PhD | 2 | 4 | 16 | 18 | 8 | 0 | 0 | 0 | 26 | 100% | 63835.2 | Two PhD researchers assigned to WP1 during m4–m16.
WP1 | P1 | Postdoc | 1 | 4 | 16 | 9 | 4 | 0 | 0 | 0 | 13 | 100% | 42134.4 | TraBERT postdoc assigned to WP1 during m4–m16.
WP2–WP3 | P2 & P3 | PhD | 1 | 16 | 39 | 0 | 9 | 12 | 3 | 0 | 24 | 100% | 63237.6518 | Shared WP2/WP3 PhD researcher; counted once in the budget.
WP2–WP3 | P2 & P3 | Postdoc | 1 | 16 | 39 | 0 | 9 | 12 | 3 | 0 | 24 | 100% | 83479.977 | Shared WP2/WP3 postdoc; counted once in the budget.
WP4–WP5 | P4 & Integration | Postdoc | 1 | 40 | 60 | 0 | 0 | 0 | 9 | 12 | 21 | 100% | 79815.0024 | WP4 postdoc during m40–m54; the same postdoc supports WP5 during m55–m60.
TOTAL |  |  |  |  | 0 | 0 | 0 | 36 | 27 | 24 | 168 |  | 511675.2449
SALARY ASSUMPTIONS |  |  |  |  | 0 | 0 | 0
Annual escalation | 5% |  |  |  | 0 | 0 | 0
Role | Y1 monthly rate | Y2 monthly rate | Y3 monthly rate | Y4 monthly rate | Y5 monthly rate | Source / note
PI | 4913 | 5158.65 | 5416.5825 | 5687.4116 | 5971.7822 | Existing workbook assumption; PI source URL retained below.
PhD | 2418 | 2538.9 | 2665.845 | 2799.1373 | 2939.0941 | Existing workbook assumption.
Postdoc | 3192 | 3351.6 | 3519.18 | 3695.139 | 3879.896 | Existing workbook assumption.
PI source URL | https://www.glassdoor.com/Salaries/germany-professor-salary-SRCH_IL.0,7_IN96_KO8,17.htm
ANNUAL LABOR COST (€)
Role | Y1 | Y2 | Y3 | Y4 | Y5 | Total
PI | 32425.8 | 34047.09 | 35749.4445 | 37536.9167 | 39413.7626 | 179173.0138
PhD | 43524 | 43161.3 | 31990.14 | 8397.4118 | 0 | 127072.8518
Postdoc | 28728 | 43570.8 | 42230.16 | 44341.668 | 46558.7514 | 205429.3794
TOTAL | 104677.8 | 120779.19 | 109969.7445 | 90275.9965 | 85972.514 | 511675.2549
COST BY WORK PACKAGE (€)
Work package | Total
PI / project coordination | 179173.0138
WP1 | 105969.6
WP2–WP3 shared team | 146717.6288
WP4–WP5 postdoc | 79815.0024
Additional WP3 personnel | 0
Additional WP5 personnel | 0
TOTAL | 511675.2449
CHECKS
Total PhD person-months | 50
Total Postdoc person-months | 58
Total PI person-months | 60
Schedule cost less summary | -0.01

## Work Plan
SEMANTRAL WORK PLAN (60m)
Inclusive month ranges. WP2 and WP3 share one team during m16–m39. The WP4 postdoc works during m40–m60 and supports WP5 during m55–m60.
WP | Pillar / objective | Work package | Start | End | Duration | Team | Core activities | Milestone / output | Y1 active months | Y2 active months | Y3 active months | Y4 active months | Y5 active months
WP0 | Enabling | Team & Infrastructure | 1 | 3 | 3 | PI; recruit project team | Recruit team; PI scientific leadership, supervision and integration across all work packages. | m4: infrastructure live | 3 | 0 | 0 | 0 | 0
WP1 | P1/O-1 | Text and semantic decoding | 4 | 16 | 13 | 2 PhD + 1 Postdoc (m4–m16) | Integrate the CBS speech corpus; establish the open-source database pipeline; corpus cleansing; readability; TraBERT dictionary; economic proficiency; decoding-wedge construction and validation. | m16: textual wedge validated; m30: WP1 papers submitted | 9 | 4 | 0 | 0 | 0
WP2 | P2/O-2 | Vocal communication | 16 | 39 | 24 | Shared WP2/WP3 team (m16–m39) | Diarization; acoustic features; pitch and volatility; clarity and pauses; decisiveness and hesitations; pre-decision vocal-signal tests. | m36: feature extraction complete | 0 | 9 | 12 | 3 | 0
WP3 | P3/O-3 | Visual and behavioural signals | 16 | 39 | 24 | WP2 team (m16–m39) | Facial, gaze, posture and gesture extraction; longitudinal affect-consistency measure; lead–lag tests against market stress. | m36: all feature extraction complete | 0 | 9 | 12 | 3 | 0
WP4 | P4/O-4 | Causal and macroeconomic effects | 40 | 54 | 15 | 1 Postdoc employed m40–m60 | High-frequency event windows; orthogonalized communication-form shocks; governor-transition DiD; local projections and proxy-SVAR. | m54: market-impact results finalized | 0 | 0 | 0 | 9 | 6
WP5 | Integration | Integration & Dissemination | 55 | 60 | 6 | WP4 team (m55–m60) | Cross-pillar synthesis; robustness checks; manuscript finalization (~8 papers); open-data release and grant closure. | m60: dissemination complete | 0 | 0 | 0 | 0 | 6
MILESTONES
Month | Milestone | [6 empty] | Responsible WP
4 | Infrastructure live | [6 empty] | WP0
16 | Textual wedge validated | [6 empty] | WP1
30 | WP1 papers submitted | [6 empty] | WP1 / PI coordination
36 | All feature extraction complete | [6 empty] | WP2–WP3
54 | Market-impact results finalized | [6 empty] | WP4
60 | Dissemination and open-data release complete | [6 empty] | WP5